## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | "2235-swen-261-02-2B-Icecaps"
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | ZS ¦ 3/17/2024 ¦ N/A
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | ZS ¦ 3/17/2024 ¦ N/A
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Fail | ZS ¦ 3/17/2024 ¦ Not implemented yet
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | ZS ¦ 3/17/2024 ¦ N/A
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | ZS ¦ 3/17/2024 ¦ N/A
Given that I have added a need to the fundBasket, the system should prevent me from adding duplicate needs to the fundBasket.
Given that I do not have a need in the fundBasket, the system should prevent me from removing needs that are not in the basket.
Given that I am on the fundBasket page, I should be able to modify the quantity of the items in my basket.
Given that I am on the fundBasket page, I should be able to modify the quantity of the items in my basket.
Given that I am on the fundBasket page, I should be able to checkout, and all the needs in my fundbasket should be removed
Given that the fundBasket is empty, an attempt to checkout should be prevented by the system.
Given that the checkout was successful, the needs in the cupboard should have their quantity modified proportional to the quantity of the need checked out.
Given that the quantity of a fundBasket item exceeds the need quantity, it should ask for confirmation for the user to proceed.
As a User I want to see a login page so I can access the website. | Given that I am on the login page when I input the correct login information(Username and Password) I get redirected to the respective main page. | Pass
Given that I am on the login page when I input the correct login information(Username and Password) for an admin I get redirected to the admin page.
Given that I am on the login page when I input the correct login information(Username and Password) for an Helper I get redirected to the Cupboard page.
Given that I am on the login page when I input the incorrect login information I get alerted my information is incorrect and remain on the login page.
Given that I am on the login page when I press to register a new account the system redirects me to the registration page.
As a admin I want to see a list of needs so that I choose how to edit them | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page.
Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Needs page when I add a new Need it add the need and updates the Needs page
Given that I am on the Needs page when I search a Need by name the system will display all relevant/partially relevant needs.
Given that I am on the Needs page when I select a need it provides fields to update the need.
Given that I am on the Needs Detail page when I edit a need the system should provide a means to save the changes done to the need
Given that I am on the Needs Detail page when I input incorrectly in one or more fields, the system should alert me of the error.
As a User I want to add multiple needs to a Need Spotlight SO THAT some needs get more attention | Given I am an admin, when I am on the Cupboard page then I see the Needs in the Need Spotlight
Given I am an admin, when I am on the Need detail page then I can modify what is the Need Spotlight
Given I am an Helper, when I am on the Main page then I see the Needs in the Need Spotlight
Given I am on the admin need detail page when I add a need to the spotlight it sets a expiration date for the need in the spotlight
As a User I want to be able to view a Blog so that I can engage within my community. | Given I am a user, when I am on the blog page then I can see a list of recent posts by other users.
Given I am a user, when I am filling out a blog post I would like to post the content to the timeline.
Given I am a user, when I am on a post I made previously I would like to be able to edit the content.
Given I am a user, when I am on a post I made previously I would like to be able to remove the post from the timeline entirely at any point.
Given I am a user, when I am on the blog page I would like to filter all the posts by a given username.
Given I am an admin, when I make a post to the blog page I would like to be flagged as an admin.
Given I am an admin, when I am on the blog page I would like to be able to remove posts that do not follow community guidelines.